## ZHD-A 106A
Report Day #: |  |  |  | 2 |  |  | Date: |  | 2018-12-05 |  |  |  |  | Well: |  |  | ZHD A / 111 |  |  | DAILY DRILLING REPORT | [11 empty] | 0.52 |  |  | Rig: |  | Sakson 602 | [5 empty] | Day mud losses: |  | 0 |  | Cumulative losses : 0 | [11 empty] | 2024-01-23
Air Gap 12.00 m |  |  | 24:00 Depth | [8 empty] | 6:00 Depth | [9 empty] | Progress: (m) |  |  |  | 0 |  | Real Time O.B. |  |  |  | 0 |  | Wind speed m/sec |  |  |  | 4 |  |  |  |  | Spud Mud |  |  |  | Material |  |  | Consumed |  |  | Stock | [5 empty] | 2024-01-24
RKB-MSL 29.52m |  |  | Last Formation top: | [8 empty] | 06:00 Operations: | [9 empty] | Av. ROP m/hr |  |  |  | 0 |  | Real ROP m/hr |  |  |  | 0 |  | Wind Direction |  |  |  | E |  |  |  |  | Wt ppg |  | 8.8 |  | Baracarb 150 / 600 | [5 empty] | 40 / 120 |  |  |  | 2010-04-17 | 1908-08-19 | 2024-01-25
MSL-S.Bed 17.2m |  |  | Duration |  |  | Move |  | From Start |  | Total |  | N/U Diverter system. | [9 empty] | Daily Cost $ |  |  | Cumulative Cost |  |  | Temp. (°C) |  |  |  | 14 |  | Wave Height (m) |  |  |  | 0.4 - 0.6 |  |  |  |  | pH |  | 10 |  | Bara-Defoam W300 / Baracor 100 | [5 empty] | 1 / 8 |  |  |  | 2009-07-06
RKB-S.Bed 46.72m |  |  | (Days) |  |  | 2 |  | 0 |  | 2 | [11 empty] | 111990 |  |  | 228022 |  |  | Forecast |  |  |  | Wind direction SE and speed 4-6 m/s, SE Wave Height 0.5m | [10 empty] | API Filt. |  | 12 |  | BaraFilm / BaraScav D | [5 empty] | 2 / 18 |  |  | Since move | 2009-05-27 17:17 | 1909-07-09 06:43
RKB-B.sect 15.3m |  |  | 2. Mud Log. Data |  |  | BK Grd gas % |  |  | Trip Gas % |  |  | Form. Gas |  |  | Conn.gas |  |  | CO2 ppm |  |  | Calc. ECD |  | ARC ECD |  |  | Temp.in/out°C |  |  | depth m |  |  | MP2 ( spm - Drlg Flow Rate,gpm -psi ) | [5 empty] | MP3 (spm - Drlg Flow Rate,gpm - psi ) |  |  |  |  | P.Visc. |  | 7 |  | BaraSure 590 | [5 empty] | 2 |  |  | Since spud | 2009-05-30 08:24 | 1909-07-06 15:36
RKB-C.sect 14.1m | [42 empty] | Y point |  | 26 |  | Barazan D | [5 empty] | 74 |  |  | LTA | 2017-01-26 13:30 | 678.4375
3.Executive summary: |  |  |  | Waiting on day light to continue skid the Rig. PJSM. Skid the Rig from well #106A over the well #111 (Total 5m). Cut & Refaced CP end, welded extension with base flange. | [38 empty] | FV |  | 51 |  | Barite | [5 empty] | 72 |  |  |  | 2009-10-03 | 1909-03-03 | 2018-12-05
[43 empty] | Gels |  | 9 / 14 / 16 |  | Barofiber / Barofiber Coarse | [5 empty] | 135 / 140
[43 empty] | LGS % |  | 1.93 |  | BDF-490 / Bentonite |  |  | 0 / 272 |  |  | 15 / 28
[43 empty] | Pf/Mf |  |  |  | CaCO3 150μ (DOTL) | [5 empty] | 0 |  |  |  |  | 1909-02-28 03:36
Run / Bit | Size |  | Make |  | Type |  | SN |  | Nozzles 1/32" |  |  |  | Depth In (m) |  | Total Daily Bit Run |  |  |  | Wt. 1000 lbs. | RPM +MTR |  | GPM |  | Press. |  | Daily Hrs. On Btm |  | Total Avg. Bit ROP |  | Total meters |  | Total Hours |  |  | I | O | D | L | B | G | O | R | MBT |  | 15 |  | Caustic Soda / Soda Ash |  |  | 6 / 8 |  |  | 54 / 46
[15 empty] | meters |  | Hours |  |  | +motor | [5 empty] | hour |  | ROP | [6 empty] | Pf/Mf MBT: Uncorr.Solids % |  | 3 |  | Citric Acid / Sodium Bicarbonate | [5 empty] | 39 / 53
[35 empty] | Pf/Mf MBT: Sand% |  |  |  | Clay Grabber / Clay Sync II | [5 empty] | 21 / 16
[35 empty] | Pf/Mf MBT: KCl % wt |  |  |  | Desco | [5 empty] | 65
[35 empty] | Pf/Mf MBT: NaCL %wt |  |  |  | Dextrid LTE | [5 empty] | 85
6.Casing data: |  | 30", 1" wall |  |  |  | 20", 94 PPF, K-55, BTC to 500m planned |  |  |  |  | 13⅜", 72 PPF,N-80Q,BTC planned |  |  |  |  | 9⅝",53.5 PPF,P-110,JFE Bear planned | [5 empty] | 7"Liner,32PPF, C-110 VA Super planned |  |  |  |  | 4.5" Liner, 15.2 PPF planned |  |  |  |  | 5.Pumps |  | Type | I: Liner; D: Displ.(bbl); B: Displ.(gal); O: Efficiency %; Pf/Mf MBT: Polyacrylamide, ppb |  |  |  | Duo Tec (DOTL) | [5 empty] | 46
|  | 85 |  |  |  | 500m/5499m TVD |  |  |  |  | 2400 m / 2012 m TVD |  |  |  |  | 3700 m MD / 2881m TVD | [5 empty] | 4850m MD / 3650m TVD |  |  |  |  | FS 5130m MD / 3836m TVD |  |  |  |  | 1 | HHF-1600 |  | I: 7"; D: 0.139; B: 5.82; O: 97; Pf/Mf MBT: Polyamine, ppb |  |  |  | Enviro-Thin / Therma - Thin / EZ-Spot | [5 empty] | 35 / 17 / 7 | 32 | Move
7. Bottom Hole Assembly: 5 | [31 empty] | 2 | HHF-1600 |  | I: 7"; D: 0.139; B: 5.82; O: 97; Pf/Mf MBT: Na+, mg/l |  |  |  | Filter-Chek | [5 empty] | 49 |  | 26"
[32 empty] | 3 | HHF-1600 |  | I: 7"; D: 0.139; B: 5.82; O: 97; Pf/Mf MBT: Total Hardness |  |  |  | Gem GPE / Hydro-Kleen | [5 empty] | 2 / 2 |  | 17"
Sensor Offset: |  | . | [29 empty] | NPT |  | Company | D: This month; B: This well; Pf/Mf MBT: Cl- |  |  |  | Glutaraldehyde 24% / HEC (DOTL) | [5 empty] | 3 / 21 |  | 12¼"
Rot. Wt: |  | P/U Wt |  |  |  | S/O Wt |  |  |  | Max Trq (K ftxlbs): | [5 empty] | Jar Hrs: |  |  | BHA(klbs) | [5 empty] | Wt below Jar (klbs): | [8 empty] | Sakson | D: 0; B: 0; O: 0; Pf/Mf MBT: API Cake |  | 2 |  | Hydro-DeFoam S (Scomi) / Oxygon | [5 empty] | 8 / 37 |  | 8½"
Time | Hrs | Phase |  | Code | [29 empty] | Weatherford Liner / FMC | D: 0; B: 0; O: 0; Pf/Mf MBT: Mud in hole |  |  |  | Pac-L / Pac-RE | [5 empty] | 60 / 62 |  | 6"
0 | [33 empty] | DOTL | D: 0; B: 0; O: 0; Pf/Mf MBT: Total circ. Vol. |  |  |  | KCL / NaCL | [5 empty] | 0 / 5 |  | Compl
0.33333 | 8 | Move |  | 11.4.4 |  | Waiting on day light to continue skid the Rig. | [27 empty] | Halliburton | D: 0; B: 0; O: 0; Pf/Mf MBT: Active |  |  |  | Radiagreen (DOTL) / SAPP (DOTL) | [5 empty] | 4 / 27
0.34375 | 0.25 | Move |  | 12.1 |  | PJSM. | [27 empty] | Odfjell | D: 0; B: 0; O: 0; Pf/Mf MBT: Reserve |  | 1001 |  | SourScav / Starcide | [5 empty] | 32 / 8
0.60417 | 6.25 | Move |  | 12.1 |  | Skid the Rig from well #106A to well #111 (Total 5m). | [27 empty] | SLB WL / Hil | D: 0; B: 0; O: 0; Pf/Mf MBT: Kill Mud / MW |  | 0 / 0 |  | SteelSeal 400 | [5 empty] | 49
1899-12-31 | 9.5 | Move |  | 12.1 |  | Cut & Refaced CP end, welded extension with base flange. Same time spud in rig on going. | [25 empty] | 8 |  | WOW / Day light | D: 13; B: 13; O: 13; Pf/Mf MBT: Daily cost |  | 2759 |  | Cum. Cost |  |  | 2759
Survey Depth MD
Inc
Azi
DLS
Remarks:
[33 empty] | P. No | M.Pump | O: Liner; D: bbl/stroke; B: gal/stroke; O: Eff. %; R: RSPM | RSP psi | RS Flow rate GPM |  | depth m MD |  | depth m TVD
[33 empty] | #1 | HHF 1600 | O: 97; R: 20 / 30 / 40
[6 empty] | O.A.M.N. | [26 empty] | #2 | HHF 1600 | O: 97; R: 20 / 30 / 40
[33 empty] | #3 | HHF 1600 | O: 97; R: 20 / 30 / 40
0
0.25 | 6 | Move |  | 12.1 |  | N/U Diverter system. Meanwhile cont'd Rig preparing for Spud in. | [25 empty] | Boat activity:
[32 empty] | CM Rose | 00:00 - 05:30 |  | I: OL; O: H2S scavenger 20 IBCs (production) - DOTL;
[35 empty] | BL | SL power pack; Winch unit & Unit cabin (to ZHD-21); HydroGuard mud 14.2ppg 50m3 (to Mercury); CaBr2 brine 15 IBCs - Halliburton; 3.5" DP 129 jts; 3.5" HWDP - Sakson;
[32 empty] | Topaz Jurong | 00:00 - 02:15 |  | I: BL; O: Waste mud 70 m3 - DOTL;
[32 empty] | Pegasus-3 | 03:00 - 03:30 |  | I: OL; O: CB w/Hydraulic oil & chiksan; Extension platform; Angle bars - SAKSON; AC (production) - DOTL;
[32 empty] | Topaz Legend | 12:45 - 21:45 |  | I: OL; O: Cmt G 38 T - SLB; Fire extinguishers 10pcs; Shaker screens 24pcs; Wire rope for Terex crane; H2S scavenger 34 IBC's; F/water 60 T; D/water 40 T; Diesel for Rig 27 T - DOTL;
[35 empty] | BL | Empty IBC 19 pcs (production) - DOTL;
[32 empty] | Pegasus-3 | 14:30 - 17:15 |  | I: OL; O: 9 1/2" BHA; Supply container; Gyro Container; Tool basket (11 lifts) - SLB;
[32 empty] | Diesel Consumption: |  | 1355 | I: Liters
Compare to Plan:
[32 empty] | 30" X 20" CCA Pressure: |  | N/A | O: psi; L: 20" x 13⅜" CCA Pressure:; O: 0; Pf/Mf MBT: psi |  | 13⅜" x 9⅝" CCA Press: |  |  |  | 350 | psi | TCA | 0 |  | psi
[32 empty] | Mud Skips |  | 12 | Full |  | 1 | Empty: |  | 11 | Standby boat |  | TOPAZ RESPONDER |  |  | Steel recovery: |  | Daily | 0 | KG | Total: |  | 0 | KG
11. HSE |  | No accident / incident Stop cards: 36 | [17 empty] | 2006-01-05 |  | Days with out LTA: |  |  |  |  | 678.4375 |  |  | Last BOP pressure test: |  |  |  |  | B: Operation look ahead:; R: Complete to install Diverter system & Function test. Drill 26" hole to section TD @+/-500m. Wiper trip as required.
Safety Topic |  | Rig up operations, pinch points, lifting operations, deck management, HW precautions… | [19 empty] | Drills: |  | 02/12/2018 – Fire / Muster Drill. | [5 empty] | Last BOP function test:
12. Bulk Data |  | Mt | Fr. Water |  |  | Dr. Water | Diesel |  | Barite |  | Bentonite |  | CMT |  | CMT blend |  | W.Mud |  | Boats bulk |  |  | Water |  |  | Dsl (MT) | Cement |  | Barite/mt |  |  | Mud |  | Hdg | Present VDL | O: Var. Load: (t) /Max.
|  | M3 | 102 |  |  | 40 | 110340 |  | 72 |  | 6 |  | 38 |  | 0 |  | 50 |  |  |  |  | 440 |  |  | 388 | 20 |  | 208 |  |  | 110 |  | 315 | 2685 | O: 3000; B: Equipment and personnel request:
Personnel on board |  |  | MAX | DOTL (Drilling)/SL |  |  | DOTL(Prod.&maint) |  | Sakson |  | SLB WL/GYRO |  |  | SLB D & M |  |  | ODFJELL |  | SLB CMT |  | SLB G/service |  |  | Halliburton |  | Zeppelin | Scomi |  |  | Weatherford |  |  | AL MASAOOD |  | I: FMC; O: Damac; D: Viking
97 |  |  | 144 | 8 |  |  | 15 |  | 48 |  | 2 |  |  | 1 |  |  | 0 |  | 2 |  | 1 |  |  | 2 |  | 0 | 0 |  |  | 0 |  |  | 2 |  | I: 0; O: 15; D: 1 | Mohammadreza Parchami / Edic Guliyev / Begench Rejepov
DO-DOTL-DLG-RPT-0000-14 Rev.0 | [29 empty] | 2018-08-30 | [21 empty] | page 1
1899-12-31
`
Note on W72: drillingsupv: Please do not write any thing in this cell related to the LTA